## Overview
NYERI COUNTY – NG-CDF FUND TRACKER ¦ 2022–2027 Parliamentary Tenure
Source: NG-CDF Board, Office of the Auditor-General (OAG), Bunge Library ¦ Amounts in KSh Millions
Constituency | MP | FY 2022/23 | FY 2023/24 (KSh M) | FY 2024/25 (KSh M) | FY 2025/26 (KSh M) | Total Allocation (KSh M) | Audit Status
Tetu | Hon. Geoffrey Wandeto (UDA) | 131.3 | 141 | 161.5 | 161.5 | 595.3 | Adverse
Kieni | Hon. Njoroge Wainaina 'Cieni' (UDA) | 165.7 | 181 | 206.6 | 206.6 | 759.9 | Qualified
Mathira | Hon. Eric Mwangi Wamumbi (UDA) | 151.9 | 168 | 188.4 | 188.4 | 696.7 | Qualified
Othaya | Hon. Michael Wambugu Wainaina (UDA) | 138.2 | 152 | 170.5 | 170.5 | 631.2 | Qualified
Mukurweini | Hon. John Kaguchia (UDA) | 138.2 | 152 | 170.5 | 170.5 | 631.2 | Unqualified*
Nyeri Town | Hon. Duncan Mathenge Maina (UDA) | 145 | 160 | 179.4 | 179.4 | 663.8 | Qualified
COUNTY TOTAL |  | 870.3 | 954 | 1076.9 | 1076.9 | 3978.1 | 0
LEGEND
Adverse | OAG found significant irregularities; unable to express an opinion
Qualified | Some issues flagged; generally compliant with minor exceptions
Unqualified* | Clean opinion issued; all expenditures supported (* limited data)
Blue figures | Hardcoded allocations from NG-CDF Board gazettes

## Audit Findings Detail
NYERI COUNTY NG-CDF – AUDITOR GENERAL FINDINGS DETAIL ¦ 2022–2027 Tenure
Source: Office of the Auditor-General (OAG) Reports – NG-CDF Constituency Accounts ¦ Bunge Library Parliament IR
Constituency | MP | FY Reviewed | Amount at Risk (KSh M) | MISAPPROPRIATIONS / ADVERSE FINDINGS | CORRECT APPROPRIATIONS / COMMENDATIONS
Tetu | Hon. Geoffrey Wandeto (UDA) | FY2022/23 – FY2023/24 | ~12.0 | • Nyaithe Primary: Ksh 1M disbursed for 8 classroom renovations; only front-wall surfaces renovated on physical inspection – incomplete works. • Kiawaithanji Primary: Ksh 1M for 8 classrooms; only 4 completed at time of audit; no remediation plan on record. • OAG unable to confirm project completion for 3 secondary school infrastructure items worth ~Ksh 6M. • Bursary register discrepancies: 14 beneficiaries listed but cheques not traced to recipients. • Bank reconciliations not prepared for Q3 FY2023/24. • Overall opinion: ADVERSE – significant unsupported expenditures. | • Bursary disbursements to primary level (Form 1–4) largely traceable and on schedule for FY2022/23. • Security lighting project at Tetu Girls completed within budget. • Procurement records for small works (below Ksh 500K threshold) maintained correctly.
Kieni | Hon. Njoroge Wainaina 'Cieni' (UDA) | FY2022/23 – FY2024/25 | ~9.5 | • Endarasha Boys: Ksh 2.1M for laboratory renovation; works stalled after contractor abandoned site – no performance bond called. • 2 road-access projects (murram) worth Ksh 4.5M: OAG noted no engineer's certificate on file for acceptance. • Stale cheques totalling ~Ksh 1.2M not cancelled within the statutory 6-month window. • Unsupported imprest surrenders worth Ksh 780K. • Overall opinion: QUALIFIED – material but not pervasive issues. | • Bursary fund fully disbursed within the fiscal year with proper acknowledgement forms for FY2023/24. • Kieni has the highest allocation in Nyeri County; absorption rate was 91% in FY2024/25 – above national average. • Gatarakwa water harvesting project completed and commissioned; community acceptance letter on file.
Mathira | Hon. Eric Mwangi Wamumbi (UDA) | FY2022/23 – FY2024/25 | ~7.2 | • Karatina High School kitchen block: Ksh 1.8M; structural works found substandard on inspection (thin wall plaster, no DPC layer). • Procurement records for Ksh 2.9M worth of projects missing from file – possible single-sourcing without board approval. • OAG flagged payments to a supplier appearing twice on vendor register under slightly different names. • Overall opinion: QUALIFIED. | • Mathira achieved 100% UDA MCA sweep – political cohesion aided faster ward-level project alignment. • Konyu Ward ECD centre (Ksh 1.6M) completed on schedule and handed over to Ministry of Education. • Bursary disbursements for FY2022/23 confirmed with signed registers at 6 secondary schools.
Othaya | Hon. Michael Wambugu Wainaina (UDA) | FY2022/23 – FY2024/25 | ~11.0 | • OAG queried Ksh 20M allocated to secondary and tertiary colleges – CDF committee could not provide methodology for identifying beneficiaries. • Ksh 3.2M disbursed for Iria-Ini VTC workshop; construction halted; no penalty clause invoked against contractor. • 3 projects marked 'completed' in internal reports but not verified on physical inspection by OAG. • Imprest of Ksh 450K outstanding beyond 30-day limit. • Overall opinion: QUALIFIED. | • Water tank installations at 4 primary schools (Mahiga area) completed and functional – OAG confirmed. • Bursary fund (FY2023/24) released within first quarter; distribution list matched payment vouchers. • Fixed asset register updated and reconciled for FY2022/23 – commended by OAG.
Mukurweini | Hon. John Kaguchia (UDA) | FY2022/23 – FY2023/24 | ~3.0 | • Minor issues: delayed procurement of classroom furniture (Ksh 1.1M order placed but undelivered by FY-end). • Imprest surrender delays noted for 2 officers in Q4 FY2022/23. • Note: Full FY2024/25 individual audit report not yet publicly released; findings above from FY2022/23 interim review. | • Overall opinion: UNQUALIFIED (clean) for FY2022/23 – only the second constituency in Nyeri to receive a clean opinion. • Rugi Ward new ablution block at primary school: completed on time, within budget, and fully equipped. • Absorption rate: 94% of allocation utilised – highest in Nyeri County for FY2022/23. • Bursary register audited clean; all cheques cashed within 90 days of issuance.
Nyeri Town | Hon. Duncan Mathenge Maina (UDA) | FY2022/23 – FY2024/25 | ~8.5 | • 3 school lab projects (Nyeri High feeder schools) worth Ksh 3.9M: OAG found bill of quantities not signed by a registered engineer. • Procurement committee quorum not attained for 2 large contracts (above Ksh 1M); retrospective approvals noted. • Ksh 2.1M bursary cheques: 11 cheques not yet presented after 6 months – possible ghost beneficiaries. • Overall opinion: QUALIFIED. | • Kiganjo primary ECD block (Ksh 1.5M): completed, inspected, and accepted by MoE. • Internal audit function active and reports submitted quarterly – commended by OAG. • Nyeri Town has an urban constituency profile; non-bursary project variety (streetlighting, ECD) praised for responsiveness.

## Allocation By FY
NYERI COUNTY – NG-CDF ALLOCATION BY FINANCIAL YEAR (KSh Millions)
Constituency | MP | FY 2022/23 | FY 2023/24 | FY 2024/25 | FY 2025/26 | 4-Year Total
Tetu | Hon. Geoffrey Wandeto | 131.3 | 141 | 161.5 | 161.5
Kieni | Hon. Njoroge Wainaina 'Cieni' | 165.7 | 181 | 206.6 | 206.6
Mathira | Hon. Eric Mwangi Wamumbi | 151.9 | 168 | 188.4 | 188.4
Othaya | Hon. Michael Wambugu Wainaina | 138.2 | 152 | 170.5 | 170.5
Mukurweini | Hon. John Kaguchia | 138.2 | 152 | 170.5 | 170.5
Nyeri Town | Hon. Duncan Mathenge Maina | 145 | 160 | 179.4 | 179.4
TOTAL |  | 870.3 | 954 | 1076.9 | 1076.9 | 0
NOTE: FY 2023/24 figures are estimates interpolated from gazette trends. FY 2024/25 and FY 2025/26 confirmed from NG-CDF Board public notices. Allocations are formula-based on registered voter population. Kieni's higher allocation reflects its larger registered voter base.